## Potential Bugs
I have identified some potential bugs on https://calculadoraonline.net. Since I do not have user requirements or documentation, the issues I found are related to UI/UX and functionality.Please note that there might be a possibility that some of these bugs may not be accurate. Before reading the bug reports, please review the following: Issue: Describes where and what the bug actually is. Steps to Reproduce: Instructions on how to find the bug, especially for new users or those unfamiliar with the website. Expected Result: What the ideal outcome should be if the bug were fixed. Actual Result: What is currently happening or being seen on the website.
Bug ID | Issue | Explanation | Steps to Reproduce | Screenshot | Expected result | Actual result | Priority
1 | Pictures fault in "Calculadora de Fração" | Some pictures show "Exemplo," while others show "Example." | 1. Open the website 2. Go to the "calculadora mathematica" 3. Open the "Calculadora de Fração" 4. Scroll down until "Adição de fração" calculator cames in | https://drive.google.com/file/d/1hRp5T6hCml1ID3i6h2C8WDZw8D_84FcC/view?usp=drive_link | All the pictures have the same result showing "Exemplo" | Some pictures showing "Exemplo" while others show "Example" | Low
2 | Typing mistakes in "Calculadora de Fração" | In some input fields, only half of the text is visible, like "Digite o numer" or "Digite o denomir." This should be fixed so users can see the full text. | 1. Open the website 2. Go to the "calculadora mathematica" 3. Open the "Calculadora de Fração" | https://drive.google.com/file/d/1Y-IXmLotabgvAoKrrbQlJeMuyMq4cYiX/view?usp=drive_link | Text is properly displayed in input fields such as "Digite o denominador" OR "Digite o numerador" | Text is not properly displayed in input fields which confuses the new user | Medium
3 | The "Reiniciar" button in "Calculadora de Diferença Percentual" sets random values (400 and 200) instead of resetting to 0,0. | The "Reiniciar" button is expected to clear or reset the input fields to 0,0. However, upon clicking, it populates the fields with random values like 400 and 200, which confuses the user as they expect a reset. | 1. Open the website 2. Go to the "calculadora mathematica" 3. Open the "Calculadora de Porcentagem" 4. Scroll down until the "Calculadora de Diferença Percentual" comes in | https://drive.google.com/file/d/1KF2RfTwA5SmGs_MUnM6Nr-WQ4dHwAgDa/view?usp=drive_link | The input fields should be cleared or reset to 0,0 when "Reiniciar" is clicked. | The input fields are set to 400 and 200 when "Reiniciar" is clicked. | Medium
4 | Inconsistent Reset Options for Calculators | Some calculators "Calculadora de Porcentagem" OR "Calculadora de Porcentagem em Frases Comuns" such as have reset buttons like "Limpar" or "Reiniciar," while others do not. All calculators with multiple input fields should include those buttons to allow users to easily clear their inputs. | 1. Open the website 2. Go to the "Calculadora Matemática" 3. Open the "Calculadora de Porcentagem" 4. Scroll down and explore 5. Open the other calculators as well | https://drive.google.com/file/d/1SRp4dJjIA_olQzKAEnaQrs_Ad_ZpoZLk/view?usp=drive_link | Every calculator with input fields should have a reset button (such as "Limpar" or "Reiniciar") so users can easily clear all the values they have entered. | Some calculators with input fields do not have a reset button, while others do. | Medium
5 | Shaking Effect on "Limpar" and "Reiniciar" Buttons | In some parts of the calculator where the "Limpar" and "Reiniciar" buttons are used, when the cursor is moved over them, they shake or jitter. However, this behavior is not consistent across all areas where these buttons appear. | 1. Open the website 2. Go to the "Calculadora mathematica" 3. Open the "Calculadora de Porcentagem" 4. Scroll down | https://drive.google.com/file/d/1wFMFqiOCQ-uFINUa8-QfobBRn_KVsM8c/view?usp=drive_link | The "Limpar" and "Reiniciar" buttons should behave consistently across the website. There should be no shaking effect when hovering over these buttons. | In some places, the "Limpar" and "Reiniciar" buttons shake when the cursor hovers over them, while in other places they do not. | Medium
6 | Resposivness error in "Gerador de Números Aleatórios" | "Gerador de Números Aleatórios Avançado" Calculator are not properly displayed on mobile & web | 1. Open the website 2. Go to the "Calculadora mathematica" 3. Open the "Gerador de Números Aleatórios" 4. Scroll down until "Gerador de Números Aleatórios Avançado" calculator cames in | https://drive.google.com/file/d/1F7OtR5gfyiMoOuUy99F4NhHVoA6lFMSQ/view?usp=drive_link | "Gerador de Números Aleatórios Avançado" are properly displayed on all devices | "Gerador de Números Aleatórios Avançado" goes to the right side while opening the mobile so it does not appears completely | High
7 | Resposivness error in "Gerador de Números Aleatórios" | "Gerador de Números Aleatórios Avançado" Calculator are not appears in the box while other calculator are appears as box | 1. Open the website 2. Go to the "calculadora mathematica" 3. Open the "Gerador de Números Aleatórios" 4. Scroll down until "Gerador de Números Aleatórios Avançado" calculator cames in | https://drive.google.com/file/d/1p2hzHa3RgMiFfG6i27OhfwZwmgtGbFr1/view?usp=drive_link | "Gerador de Números Aleatórios Avançado" appears in the box just like the "Gerador de Números Aleatórios Simples" have. | "Gerador de Números Aleatórios Avançado" appears like a text and an input field but the other calculator appears in the box and have the box shadow which enhances the UI experience | Low
8 | Text display error in the "Calculadora Cientifica" | While using the "Calculadora Cientifica" , this text "Insira uma expressão abaixo" are not properly displayed in the mobile. | 1. Open the website 2. Go to the "Calculadora mathematica" 3. Open the "Calculadora Cientifica" | https://drive.google.com/file/d/1dr5lszlTsQgV-8_tjz_VmxFyVSaN3g7q/view?usp=drive_link | This text "Insira uma expressão abaixo" are properly displayed & appears on the top right corner inside the calculator & its not possible to display properly then it must be in 2 lines while using the mobile | Only "Insira uma" are displayed while using the "Calculadora Cientifica" and the remaining text is hide | Low
9 | "Calculadora Cientifica" errors when trigonometric functions lack a closing bracket. | When using the "Calculadora Cientifica" and selecting a trigonometric function (sin, cos, tan), the calculator automatically inserts an opening bracket but does not handle the absence of a closing bracket, leading to an error | 1. Open the website 2. Go to the "Calculadora mathematica" 3. Open the "Calculadora Cientifica" | https://drive.google.com/file/d/1CJYbW0NWU_o1PHyhz1RNnYjrFAondsow/view?usp=drive_link | The calculator should either provide the correct result without requiring a closing bracket | After entering a number following a trigonometric function (e.g., sin), the calculator shows an "undefined" error unless a closing bracket is manually added | High
10 | Resposivness error in "IMC Calculadora" | The table "Tabela de IMC usada para calcular IMC para adultos" overlays the text when viewed on mobile devices. | 1. Open the website 2. Go to the "Calculadora de Saúde 3. Open the "IMC Calculadora" 4. Scroll down until "Tabela de IMC usada para calcular IMC para adultos" calculator cames in. | https://drive.google.com/file/d/1X1Tq3wHYxLWJFcyF3MbMl3jmpGr9UJvK/view?usp=drive_link | The table should be responsive and not overlap with the text on mobile devices. | On mobile, the table overlays the text, making it hard to read. | Medium
11 | Lack of responsivess in "IMC Calculadora" | The table "Tabela de IMC para crianças e adolescentes (de 2 a 20 anos) para calcular IMC" shifts to the right side on some mobile devices and sometimes overlays text. | 1. Open the website 2. Go to the "Calculadora de Saúde" 3. Open the "IMC Calculadora" 4. Scroll down until "Tabela de IMC usada para calcular IMC para adultos" calculator cames in. | https://drive.google.com/file/d/19umENj6keFakP-shIklo1f4LUj3U66BW/view?usp=drive_link | The table should stay aligned properly without overlapping the text on all mobile devices. | On some mobile devices, the table shifts too far to the right or overlays the text. | Medium
12 | Visual inconsistency in the UI button styling in "IMC Calculadora" | In the "IMC Calculadora," when using the "Conversor de Altura/Peso" on mobile devices, the "Altura" button is only partially highlighted, while the "Peso" button is fully highlighted. This issue does not occur on the desktop version. | 1. Open the website 2. Go to the "Calculadora de Saúde" 3. Open the "IMC Calculadora" 4. Scroll down until "Tabela de IMC usada para calcular IMC para adultos" calculator cames in. | https://drive.google.com/file/d/15aXD7IVuq6ctSdOYAZhw66k3aauBsr_w/view?usp=drive_link | Both "Altura" and "Peso" buttons should have consistent coloring that fully fills the respective boxe | When switching between "Altura" and "Peso," the color of the "Altura" button does not fill the box completely, but the "Peso" button fills the box entirely | Low
13 | Inconsistent Placeholder Font Style in "Calcular IMC" | On the "IMC Calculadora", "Calcular IMC" has two input fields: "altura" and "peso." The placeholder text for these fields is "Tua altura" and "Seu peso." These placeholders use a bold font, which is different from the lighter font style used for other placeholders on the website. | 1. Open the website 2. Go to the "Calculadora de Saúde" 3. Open the "IMC Calculadora" | https://drive.google.com/file/d/1DgHjomSitwXT5kYxvqe7giWTlo8W2M5K/view?usp=drive_link | The placeholder text in all input fields, including "Tua altura" and "Seu peso," should use a consistent font style with the lighter font used for other placeholders on the website. | The placeholder text in the "altura" and "peso" fields is bold, while other placeholders on the website use a lighter font. | Low
14 | Inconsistent Button Style in "Calcular IMC" | In the "Calcular IMC" calculator, the "Metric" and "Imperial" buttons have a different style compared to other buttons on the website | 1. Open the website 2. Go to the "Calculadora de Saúde" 3. Open the "IMC Calculadora" | https://drive.google.com/file/d/19iWmGv33flRwwMXnqZg1UWurDNfH5bDU/view?usp=drive_link | The "Metric" and "Imperial" buttons should have the same style as the other buttons on the website to maintain a consistent user interface. | The "Metric" and "Imperial" buttons in the "Calcular IMC" calculator have a different style from the other buttons on the website. | Low
15 | "IMC Infantil" calculator is not working | When setting up the "Idade" ,"Altura " ,"Peso " & and click the "Calcular o IMC" , no result showing in my screen | 1. Open the website 2. Go to the "Calculadora de Saúde" 3. Open the "IMC Infantil" | https://drive.google.com/file/d/1HASkMP3taaov43sG127JgxYYsYVVK4-y/view?usp=drive_link | The calculator should display the calculated IMC result based on the provided inputs after clicking the "Calcular o IMC" button. | After entering the required data and clicking "Calcular o IMC," no result appears, and the calculator does not function as expected. | High
16 | The lack of range guidance in "IMC Infantil" | There is no range guidance for valid inputs (e.g., "Insira um valor entre --- e ---") under the "Altura" and "Peso" fields. | 1. Open the website 2. Go to the "Calculadora de Saúde" 3. Open the "IMC Infantil" | https://drive.google.com/file/d/1WrpVCVpioLzaDjlQ6reHtlZlAnRKgjsv/view?usp=drive_link | There should also be range guidelines such as "Insira um valor entre --- e ---" for "Altura" and "Insira um valor entre --- e ---" for "Peso" to help users input valid data. | No range guidelines appear for the "Altura" and "Peso" fields to guide users on valid input values. | Medium
17 | No search suggestion feature is available to guide users. | In the website's search bar, when users search for calculators & make slight typos or incomplete entries no dropdown suggestions appear to guide the user to the correct calculator names. | 1. Open the website 2. Go to the Search bar which appears on the top right corner 3. Search for any calculator name in Portugese | https://drive.google.com/file/d/1F23X5UTDwlN03k8BLHbhyywR1c8Ghqoc/view?usp=drive_link | A dropdown menu should appear with suggested calculator names as the user types, helping them find the correct calculator even if the search input is not exact. | No dropdown suggestions appear when typing incomplete or slightly incorrect calculator names in Portuguese, and no search results are shown. | High
18 | Automatic Entry of Calculator Values from Search | When text is entered into the "Pesquisa" , it automatically inputs certain buttons (e.g., "X", "Y", "I", "E" ", " "." "/") into the calculator. This occurs even though only text should be entered into the search field. | 1. Open the website 2. Go to the Search bar which appears on the top right corner 3. Type these buttons into the "Pesquisa" | https://drive.google.com/file/d/1PCclMj-8FFKmeyWwbfsiHKfAKH-0vWNG/view?usp=drive_link | Typing text in the search box should not appear into the calculator. The calculator should only respond to what you enter directly into it. | Typing in the search box causes random calculator buttons to appear in the calculator. | High
19 | Misaligned Formula "Calculadora de Juros Compostos" on Mobile | On the "Calculadora de Juros Compostos" page, there is a formula "Fórmulas de juros compostos" (Mf = Mi(1 + i)n). Below the formula, each term (Mf, Mi, i, n) is explained. However, when viewed on a mobile device, the text next to each term (Mf, Mi, i, n) is not properly aligned, causing readability issues. | 1. Open the website 2. Go to the "Calculadora Financeira" 3. Open the "Calculadora de Juros Compostos" 4. Scroll down until "Fórmulas de juros compostos" calculator cames in | https://drive.google.com/file/d/1XFTB07Y2TGWe7FPsDuF41kObvTpo-bSj/view?usp=drive_link | The explanation text for "Mf", "Mi", "i", and "n" should be properly aligned on mobile devices for better readability and understanding. | On mobile, the explanation text for "Mf", "Mi", "i", and "n" is misaligned, making it difficult to understand the formula. | Low
20 | Inconsistent Heading Styles in "Calculadora de taxa de juros" | In the "Calculadora de taxa de juros," some headings are bold while others are not. Additionally, some headings have different font sizes, and the overall alignment of headings is inconsistent, causing a lack of uniformity in the presentation. | 1. Open the website 2. Go to the "Calculadora Financeira" 3. Open the "Calculadora de taxa de juros" 4. Scroll down and explore this section | https://drive.google.com/open?id=1HPrBpMBpJe58yJrqfAuhgjQyep15UXAg&usp=drive_copy | All headings should have consistent formatting, including font size, boldness, and proper alignment, to maintain a uniform and professional appearance. | Headings are inconsistently formatted, with some being bold and others not. Some headings have larger font sizes, and the alignment of headings is uneven. | Low
21 | Placeholder Text Not Fully Visible in "Calculadora de Juros" | In In the "Calculadora de Juros," the input field labeled "Período de Tempo (meses) (Opcional):" has a placeholder text that is too long for the box. | 1. Open the website 2. Go to the "Calculadora Financeira" 3. Open the "Calculadora de Juros" 4. Check the placeholder text | https://drive.google.com/file/d/1ndzYKoxoQuOLOSnrsnSe032t2SHOBmwe/view?usp=drive_link | The entire placeholder text "Digite o período de tempo em meses (opcional)" should be visible inside the input box, either by resizing the box or adjusting the text size. | The placeholder text is cut off and not fully visible within the input box. | Low
22 | "Calculadora de Juros" Output Values Overflowing on Mobile | On mobile devices, the output values, such as "Juros Compostos" and "Montante Total (Investimento Inicial + Juros Compostos)," are displayed outside of the designated box, causing layout issues. | 1. Open the website 2. Go to the "Calculadora Financeira" 3. Open the "Calculadora de Juros" 4. Fill all the input fields 5. Enter "Calcular" | https://drive.google.com/open?id=16gWBiWepj4b-O0ZH5ePpNYsC0RK6cMKO&usp=drive_copy | The output values should be fully contained within the designated output box on mobile, ensuring proper alignment | On mobile, the values "Juros Compostos" and "Montante Total (Investimento Inicial + Juros Compostos)" are not contained within the output box and spill outside. | Medium
23 | Oversized Dropdown Menu for Date selection in "Calculadora de Dias" | In the "Contagem de Dias entre Datas" calculator, there are two fields: "Data de Início" and "Data de Término." Each of these fields contains additional dropdown menus to select the day & month. However, the dropdown menu for selecting the date is excessively large, causing a poor user experience, especially on smaller screens. | 1. Open the website 2. Go to the "Outra Calculadora" 3. Open the "Calculadora de Dias" 4. Fill all the input fields | https://drive.google.com/file/d/1z4r_wcah5l-GTYK-rLiBsm2LTVKAnW_2/view?usp=drive_link | The dropdown menu for the date and month should be appropriately sized for better usability | The dropdown menu for the date in both "Data de Início" and "Data de Término" is too large, making it difficult to use and leading to a bad user experience. | Medium
24 | Inconsistent Visual Highlighting of Input Field in "Calculadora de Dias" | In the "Adicionar ou subtrair de uma data" calculator, the "Selecione uma data" field is visually highlighted with a different style (such as a border or background color), which is not consistent with the other input fields like "Anos," "Meses," "Semanas," and "Dias." | 1. Open the website 2. Go to the " Outra Calculadora" 3. Open the "Calculadora de Dias" 4. Scroll down until the "Adicionar ou subtrair de uma data" arrives | https://drive.google.com/open?id=19QVx_kRfcZOm14grlCcPjULoUBl4vGV_&usp=drive_copy | All input fields should have consistent visual styling to maintain uniformity | The "Selecione uma data" field is visually distinct from other fields, | Low
25 | Misaligned "Limpar" and "Calcular" Buttons in "Calculadora de Horas" | In the "Calculadora de Horas", the "Limpar" and "Calcular" buttons are not properly aligned. The "Limpar" button is positioned slightly higher than the "Calcular" button, creating an uneven layout. | 1. Open the website 2. Go to the "Outra Calculadora " 3. Open the "Calculadora de Horas" | https://drive.google.com/file/d/14EZPkybP9EzdusYdPiUdtKOd1a79rjKT/view?usp=drive_link | Both buttons should be aligned horizontally at the same level for a cleaner and more visually consistent interface. | The "Limpar" button is placed slightly above the "Calcular" button, causing a misalignment. | Low
26 | Output Values Appear Outside the Box in "Calcular horas entre dias" | In the "Calcular horas entre dias" calculator, there are two input fields: "Data e Hora de Início" and "Data e Hora de Término," where users can set the start and end date and time. After filling in both fields, the output values are displayed outside the box on mobile devices, disrupting the design. | 1. Open the website 2. Go to the "Outra Calculadora" 3. Open the "Calculadora de Horas" 4. Scroll down until "Calcular horas entre dias" calculator cames in 5.Fill out all the input fields and press "Calcular Horas" | https://drive.google.com/file/d/1kagi90_-LlMAJK2nG_oadpeUatBBESpJ/view?usp=drive_link | The output values should fit properly inside the box, both on mobile devices and the web, to maintain a clean layout. | The output values overflow outside the box after entering the start and end date and time. | Medium

## Suggestions to improve
Calculators Name | Suggestions
# | All internal links provided on the website must open in a new tab.
Calculadora de Juros Compostos | The points under "Prós" and "Contras" start directly below the headings. They are placed too far to the right, about 3-4 inches away. The text should start right below the headings for better alignment and readability.
Outras Calculadoras | The website has a section on the right side called "Outras Calculadoras" with links to calculators.Since these calculators are already listed in the navbar, this section is not needed I suggest removing it to make the site cleaner and easier to use.
Outras Calculadoras | The website has a section called "Outras Calculadoras" on the right side, which links to different calculators. For some calculators, like "Calculadora Normal," this section appears at the top, while for others, like "Calculadora Científica," it appears at the bottom. I suggest removing this section entirely. If it cannot be removed, then it should be moved to the top of all calculator pages for consistency.
IMC Calculadora | All the buttons on the website should have a consistent style. For example, the "Usar Conversor" button and the "Calcular o IMC" button currently have different styles, which looks inconsistent. I recommend standardizing the button styles to improve the overall design and user experience.
# | Website is mainly for Portuguese-speaking users, and you've done great work on it. However, for English-speaking users, it would be helpful if the calculator outputs were fully translated into English. It's okay if other content, like content, images, isn't translated, but the calculators' results should be correctly translated to ensure English users can understand them clearly.
# | At this stage, I think it’s better to focus on quantity rather than quality, such as images and tables for the calculators. The main task of a calculator is to provide accurate outputs, not false ones. If your calculators deliver the results users need but don’t initially include pictures or charts, that’s fine. Visual elements can take time to prepare, so it's more important to prioritize adding functional calculators first.